## Product Roadmap
| ID | Category | Feature | Description | Wireframes | Approved by HCP (Abhinav) | Legal Approved (Max/ Richard) | Branding Approved (Andrew) | Behavioral Approved (TDL) | UI Approved (Libeo + TDL) | Development Completed (Libeo) | Dependencies
v1 |  | Onboarding | Intro Screens | Intro screen(s) explaining the value prop of the app and selecting language | Y | No | No | No | No | No | No
v1 |  | Onboarding | Location/Notification Permissions | App permission request (GPS ONLY / Notifications) during onboarding + instructions on how to activate them if they turn them off/user clicks No by mistake (to be integrated whenever they open the app) | Y | No | No | No | No | No | No
v1 |  | Onboarding | "Your Data Usage" Permissions | Consent to share with other users of the app + description and ability to opt-out of the MILA + POP-level data | Y | No | No | No | No | No | No
v1 |  | Onboarding | Quick Assessment | Gather information on user (age, conditions, covid history) + TOP ACTION CARD + RECOMMENDATIONS if user has symptoms in onboarding | In Progress | No | No | No | No | No | No
v1 |  | Core | Self-Diagnostic Intake | Including Severe + Mild Symptoms, to be accessed after onboarding if assessment shows symptoms, or accessed anytime from dashboard. | Y | No | No | No | No | No | No
v1 |  | Core | Self-Diagnostic Results | For mild + severe situations. COVID Test phone numbers need to be geolocated to user region + functionality to geolocate nearest testing centers + ability to revert the diagnostic | N | No | No | No | No | No | No
v1 |  | Core | Self-Diagnostic Results for HCP | A HCP should call supervisor - different output than normal user. | N | No | No | No | No | No | No
v1 |  | Core | Panel - Dashboard | User sees if they are normal risk or high risk as well as the behaviors that they should be engaging in given their risk level and that province's guidelines at that time (RECOMMENDATIONS). User can also access setttings. User can see their ACTION CARDS - what actions they should be taking in app. Initial Action Cards: 1. Featured "Resource" - dynamic, needs to be taken from the Resources - will be typically an article that is positive/curated. (Frequency: Weekly ¦ Behavior: Once read, dissapears from Dashboard - can always be accessed in Resources) 2. Received COVID19 result - Opens confirm test result (negative/positive + 2 consents) (Freqency: Permanent, but low priority, 'grayed' out so it doesnt' seem it's something users NEEDs to do ¦ Behavior: Once confirmed negative stays grayed out; once confirmed positive and cured, can never reappear) 3. Improve Your Risk Assessment (Additional questions) - additional questions on behaviors - to be done only once (Frequency: Shows up right away as something that needs to be done, Behavior: Once completed, never shows up; if opened up without being finished, stays active, as before) 4. Self Check (Have symptoms?) - Shows up in red, before anything (and affects entire interface) if the user said have symptoms from the start. If not, shows up greyd out (Frequency: Shows greyed out, above covid test, always on (unless symptoms at start); Behavior: Once completed with no result, greyed out. If completed and mild symptoms, greayed out and name/instruction changed to Feeling better? Check your symptoms again) 5. Share the App - Opens native share for now. later referral dashboard. always active and on. 6. Update Health Status - Asks users to update if they have come into contact with covid 19 people, if they've traveled, etc. (questions we had in onboarding, withotu age, sex or HCP) (Frequency: Shows greyed out, at the bottom. we pop-up it to active every 14 days; Behavior: once completed, stays greyed out and moves at bottom). | In Progress | No | No | No | No | No | No
v1 |  | Core | Panel - Resouces + "Featured resource" | Gov resources accessible - where to call for help (localized), about COVID, prevention, etc. Similar/same as CanadaCOVID19?. "FEATURED" Resource - will be always one that is top of the other 'boring' resources and will be a quote from a positive article that's curated + link to the article. This will also become an 'action card' that SHOWS UP EVERY 1-2-3 days as RECOMMENDATION (on the dashboard) | N | No | No | No | No | No | No
v1 |  | Core | Panel - Settings | Ability to see what your have activated and WHY (and opt-out if you want to from MILA + gov), language of the interface, health status - prexisiting conditions, age, covid questions. | Y | No | No | No | No | No | No
v1 |  | Behaviors | Panel - My Impact | Future screen that will show impact - v1 will just be a "dumb" screen - Top: "How are we flattening the curve", general image of the curve being flattened, and short description talking about how the app will show individual impact as more people start using it and roll out new features. Bottom: Button to open native share (same as the 'share action' on the dashboard) | N | No | No | No | No | No | No
v1 |  | Risk | Static Risk Level Changes (Based On Quick Asessment) | Risk level (high/normal) based on age/pre-conditions + provincial government parameters for that day. | - | No | No | No | No | No | No
v1 |  | Behaviors | Static Recommendations On Behaviors According to Risk Level | Dashboard displays recommanded behaviors (RECOMMENDATIONS) based on risk level and government (provincial) parameters. + Ability to see WHY am I getting these recommendations (tooltip) | - | No | No | No | No | No | No
v1 |  | Sharing | Share Application | Basic share functionaliy (email + sms) with corresponding copy (according to language seleced) | - | No | No | No | No | No | No
v1 |  | Core | Basic Notifications | If user has notifications on but location off, let user know, show instructions on how to activate. Push notification to get user to upgrade if v installed is older than 3 (?) days. Push notification if user did not do quick assessment (abandoned after activating push notifications) | - | No | No | No | No | No | No
v1 |  | Core | Positive COVID19 Test Result - Self-Reported | *Action Card* - Ability to self report a positive diagnostic, with NO verification from authorities. Ability to revert (if user error). This would be fed into the model, marked as 'self reported' and not sent out to the network. | N | No | No | No | No | No | No
v1 |  | Risk | Additional Model Training Questions | "Action Card" - User can answer questions on their habits - (whether they go outside or not, whether they wear masks, how far away they sit from ppl) biological gender, etc. | Maybe | No | No | No | No | No | No
v1 |  | Optimization | Analytics | Ability to see where users have been dropping off, in-app interactions, length of session, etc (Mixpanel?) | - | No | No | No | No | No | No
v1 |  | Optimization | A/B Testing Capabilities | Ability to A/B test various features of the app and major redesigns (showing risk score or not scores) | - | No | No | No | No | No | No
v1 |  | External | Long-Form Privacy Policy | Long form privacy policy, to be linked from the app (on website, external) | - | No | No | No | No | No | No
v1 |  | External | Website - with FAQ, Landing Page | Website presenting the app, value prop + email capture. or phone number to link to send out link to phone/email. | - | No | No | No | No | No | No
|  | Core | Delete Data From MILA | Ability to 'delete' your data
BACKLOG
v2 |  | Risk | Dynamic Risk Level Changes (Based on Model) | Risk level will change according to the model.
v2 |  | Behaviors | Dynamic Recommendations On Behaviors According to Risk Level | Behaviors will be recomanded based on the risk level - which is dynamic in v2. Initial nudge engine.
v2 |  | Behaviors | Location Based Nudging | Users would be nudged to reduce out of home activities if 1) gov lockdown "level" is high 2) they went out more than 2k away from house within 2? days? Need to consider density of devices - how can we avoid false positive due to walks, age (if they're over 70 shouldn't go out AT ALL?), all other conditions need to be established |  | No | No | No | No | No | No
v2 |  | Core | Panel - Notifications | User can see history of 'notifications' (does not mean they were also pushed) such as - how many people recovered and are now immune, number of new cases in their province, country, links to livestream on provincial/federal announcements, etc. Ability to 'unsubscribe' and remove notifications you don't want to see there.
v2 |  | Diagnostic | Positive COVID19 Test Result - Verified by Officials | User can see the results of the COVID19 test (sent via email/sms link with a token that allows to ?) in the app, and is asked to share the results anyonymous to be part of the model + help others avoid getting sick. | [7 empty] | Healthcare infrastructure + training
v2 |  | Diagnostic | HCP Backend for Sending COVID19 Test Results | - Country wide system for HCP to input test results and send it to users - Support line 24/7 for system problems (technical assistance call center) + tickets - Public facing web interface for checking results OR force them into app download- or strongly nudge - Call-in number for receiving results?
v2 |  | Diagnostic | Step-by-Step Guidance When Tested Positve | Currently, NPs call the positive patient and describe to them what they need to do - they. 'train' them. If we replace that call, we need to do this in the app + have a way to 'record' that they understood and acknowledge their responsabilities.
v2 |  | Diagnostic | Positive COVID19 Test Result (Retroactive) - Verified by Officials | Retroactive results (email OR phone #, result positive/negative, can be entered in a system, messaging all users who tested positive with a text/email that asks to download the app or (if already isntalled) opens it to 'record'/share their diagnostic
v2 |  | Sharing | Panel - Referral Screen | Tracks the referrals from sharing the application + shows up in notification.
v2 |  | Onboarding | Behaviours questionnaire | Ask users: are you working outside your home, interacting with public, wearing a mask, etc. Needs a page setup to capture, and an action card created
v3 |  | Core | "Passport" Functionality | People who have tested positive, then negative (twice?) are now 'immune' - app becomes somethign else? TBC if people really are immune, for how long, etc.

## Project Management
COVI PROJECT MGMT DASHBOARD
MILESTONE | CATEGORY | DESCRIPTION | START | END | DAYS | OWNER | PROGRESS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
[8 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
FRONT END/DESIGN/UI
User Flows Completed | Development |  | 2020-04-01 | 2020-04-05 | 4 | Libeo | 100% | bar: WEEK 2 M to WEEK 2 T
Wireframes Completed | UI/UX |  | 2020-04-01 | 2020-04-06 | 5 | Libeo | 80% | bar: WEEK 2 M to WEEK 2 T
Visual Identity Guidelines/Assets Completed | Marketing/Branding |  | 2020-04-05 | 2020-04-07 | 2 | Broadside9 | bar: WEEK 2 M to WEEK 2 T
Mockups Completed | UI/UX |  | 2020-04-04 | 2020-04-07 | 3 | Libeo | 60% | bar: WEEK 2 M to WEEK 2 T
BEHAVIORAL
Target Behavior Identified | Behavioral | Identify the key user behaviors that are both achiavable and likely to lead to a decrease in Rnaught given current technolgical and model constraints of v1 | 2020-04-01 | 2020-04-05 | 4 | TDL | bar: WEEK 2 M to WEEK 2 T
Behavioral Barrier Survey Completed | Behavioral | A survey probing Canadians on key points of friction in the application, with a particular focus on privacy and onboarding | 2020-04-02 | 2020-04-06 | 4 | TDL | bar: WEEK 2 M to WEEK 2 T
Interventions Researched | Behavioral | Perform literature reviews and engage expert practitioners to inform design of interventions ("nudges") that will reduce the barriers to the user engaging in the behaviour and amplify the drivers towards these behaviours | 2020-04-01 | 2020-04-03 | 2 | TDL | bar: WEEK 2 M to WEEK 2 T
User Flows + Mockups Behavioral Audit Completed | Behavioral | Behavioral audits to determine if target behaviors identified will be met based on identified interventions | 2020-04-01 | 2020-04-08 | 7 | TDL | bar: WEEK 2 M to WEEK 2 T
User Flows + Mockups + App Copy + Privacy Behavioral Tests Performed | Behavioral | Experiments to determine user behaviors and atittudes towards current user flows, designs, drop-offs - validating the most important privacy concerns from V1 (e.g. gender) and testing out onboarding variations to find highest activation event rate. Including first iterations of the the copy for the app. | 2020-04-06 | 2020-04-09 | 3 | TDL | 40% | bar: WEEK 2 M to WEEK 2 T
Branding / Value Proposition Behavioral Tests Performed | Behavioral | Various tests to validate value proposition and how it resonates with Canadian concerns/personas. | 2020-04-01 | 2020-04-09 | 8 | TDL | bar: WEEK 2 M to WEEK 2 T
v1 Nudge Engine Developed | Behavioral | Creation of v1 behavioral nudge engine - based on user surveys, behavior change frameworks. current state of ML model, and epidemiological guidelines (provincial) | 2020-04-01 | 2020-04-08 | 7 | TDL | bar: WEEK 2 M to WEEK 2 T
DEVELOPMENT
Infrastructure setup completed | Development |  | 2020-04-03 | 2020-04-09 | 6 | Libeo | 100% | bar: WEEK 2 M to WEEK 2 T
Backend Development (App) Completed | Development |  | 2020-04-03 | 2020-04-08 | 5 | Libeo | 80% | bar: WEEK 2 M to WEEK 2 T
Front-End Development (App) Completed | Development |  | 2020-04-03 | 2020-04-08 | 5 | Libeo | 60% | bar: WEEK 2 M to WEEK 2 T
Website Landing Page Developed | Development |  | 2020-04-06 | 2020-04-10 | 4 | Broadside9 | 40% | bar: WEEK 2 M to WEEK 2 T
App Store Submission Done (release date 4/11 - G Play + iOS) | Development |  | 2020-04-08 | 2020-04-09 | 1 | Libeo | bar: WEEK 2 M to WEEK 2 T
COPY
Branding Guidelines Completed | Marketing/Branding | All branding and design language completed. | 2020-04-01 | 2020-04-06 | 5 | Broadside9 | 100% | bar: WEEK 2 M to WEEK 2 T
App Copy Completed (French) | Marketing/Branding |  | 2020-04-03 | 2020-04-07 | 4 | Libeo/Broadside9 | 80% | bar: WEEK 2 M to WEEK 2 T
App Copy Completed (English) | Marketing/Branding |  | 2020-04-07 | 2020-04-08 | 1 | Libeo/Broadside9 | bar: WEEK 2 M to WEEK 2 T
Privacy Policy Completed | Legal | Privacy policy created, vetted, as well as all policy implications. | 2020-04-01 | 2020-04-10 | 9 | Max/Richard | 60% | bar: WEEK 2 M to WEEK 2 T
Website Copy Completed | Marketing/Branding |  | 2020-04-08 | 2020-04-09 | 1 | Libeo/Broadside9 | bar: WEEK 2 M to WEEK 2 T
QA
Internal QA | Development |  | 2020-04-07 | 2020-04-10 | 3 | Libeo | bar: WEEK 2 M to WEEK 2 T
QA - before initial App Store Submission (HCP, Legal, branding, Behavioral, UI, Dev) | Team | Test (20-30 users) before app submission and sign-off from each team lead. | 2020-04-07 | 2020-04-08 | 1 | Each lead | 100% | bar: WEEK 2 M to WEEK 2 T
QA (While in app store process) | Team | Stress test while app is in app store 100+ users, various devices. Libeo needs to perform stress testing. | 2020-04-08 | 2020-04-10 | 2 | Each lead | 80% | bar: WEEK 2 M to WEEK 2 T
Final QA Complete + App Updated | Team | Sign-off from each team lead on any changes done before update | 2020-04-10 | 2020-04-11 | 1 | Each lead | 60% | bar: WEEK 2 M to WEEK 2 T
MACHINE LEARNING
Initial Requirements For Data Collection Delivered v1 (to be integrated) | ML | What data should be collected and how in v1 - to make sure we're actually collecting all the right info from the start, in the RIGHT way. e.g. Geolocation information sent to machine learning server is chosen large enough to contain at least 1000 people. | 2020-04-01 | 2020-04-05 | 4 | MILA | 100% | bar: WEEK 2 M to WEEK 2 T
Initial Model Integrated in App Validated | ML | Validate how the integration has been done - are the right things being recorded at the right times to inform the model? | 2020-04-05 | 2020-04-08 | 3 | MILA | 80% | bar: WEEK 2 M to WEEK 2 T
LAUNCH
Federal and Government Approval | Legal |  | 2020-04-11 | 2020-04-11 |  | MILA | bar: WEEK 2 M to WEEK 2 T
Website Launched | Development |  | 2018-04-05 | 2018-04-08 | 3 | Broadside9 | 100% | bar: WEEK 2 M to WEEK 2 T
App Launched (Downloadable) | Development |  | 2020-04-12 | 2020-04-12 | 0 | Libeo | 80% | bar: WEEK 2 M to WEEK 2 T
Day 0 PR Launched | Marketing/Branding | Broadside9 detailed marketing and rollout plan. | 2020-04-12 | 2020-04-12 | 0 | Broadside9 | 60% | bar: WEEK 2 M to WEEK 2 T
Marketing Campaigns Rolled Out | Marketing/Branding |  | 2020-04-13 | 2020-05-13 | 30 | Broadside9 | 40% | bar: WEEK 2 M to WEEK 2 T

## Checklist
MODEL
v1 | Model | Risk Model Accounts for Verified COVID-19 Test
v1 | Model | Risk Model Accounts for Self-Reported Symptoms
v1 | Model | Risk Model Accounts for HCP Users | Should the model account for the fact that HCP who work with COVID-19 patients will be in proximity with them more often + should we account for higher degree of protection?
MARKETING
v1 | Marketing | Online Presence | Landing page for the app, with FAQ, endorsments, facebook, instagram profiles, etc
v1 | Marketing | Branding Guidebook + Visual Identity | Visual identity + branding, name, etc.
v1 | Marketing | Posters with QR Codes, Social Badges and other collateral
| Marketing | App Store Preview - Preview Screenshots + Copy in French and English | Super careful on how this is framed.
| Marketing | Get featured on Canadian AppStore (App Home) | https://www.iphoneincanada.ca/app-store/government-canada-app-store-flatten-curve/
INFRASTRUCTURE & QA
v1 | Infrastructure | Mixnet + Filesystem Up and Running
v1 | Infrastructure | Compliance with fed/provincial requirements
v1 | Infrastructure | App Package + Signature From MILA
v1 | Infrastructure | ??
| QA | QA Like Crazy | Get list of 95% type of devices in Canada, get 50-100 people QA'ing via TestFlight, all functionality